## Gantt Chart
StreamList development Gantt chart
Proposed estimates. Week 1 = project start. One week = five working days.
No course dates were provided. Overlapping tasks require sufficient team capacity.
Duration inputs are amber. Start and finish days update from predecessor tasks.
Task # | Task | Days | After Tasks | Start day | Finish day | SRS reference | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Review SRS and confirm scope | 2 | — | 1 | 2 | Sections 1–4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Create Gantt chart (Rommel) | 2 | 1 | 3 | 4 | Program design assignment | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Create wireframe (Charles) | 3 | 1 | 3 | 5 | FR14; UI Section 3.1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Check provider and payment access | 4 | 1 | 3 | 6 | FR16; Section 3.3–3.4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Review design and set up repository | 2 | 2, 3 | 6 | 7 | FR14; Section 4.6 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Present design and upload files to GitHub | 2 | 5 | 8 | 9 | Program design assignment | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Build app, database and secure foundation | 5 | 4, 5 | 8 | 12 | Section 3.3; Sections 4.1–4.2,4.5–4.6 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Build registration, login and logout | 4 | 7 | 13 | 16 | FR1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Build profiles and account settings | 3 | 8 | 17 | 19 | FR12 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Build monthly subscription management | 5 | 9 | 20 | 24 | FR2; Section 4.1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Connect movie metadata and provider APIs | 5 | 7 | 13 | 17 | FR4,6,16 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Build movie search and filters | 4 | 11 | 18 | 21 | FR3 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Build movie details and provider launch | 3 | 12 | 22 | 24 | FR5,6 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Build personal watchlists | 3 | 8, 13 | 25 | 27 | FR7 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
15 | Build viewing history | 3 | 13, 9 | 25 | 27 | FR9 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
16 | Build movie recommendations | 4 | 14, 15 | 28 | 31 | FR8 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
17 | Build availability notifications | 4 | 14, 16, 9 | 32 | 35 | FR10; Section 3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
18 | Build parental profiles and restrictions | 4 | 9, 13 | 25 | 28 | FR11 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
19 | Build administration and support tools | 5 | 10, 11 | 25 | 29 | FR13; Section 3.4 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
20 | Finish responsive UI and accessibility | 4 | 17, 18, 19 | 36 | 39 | FR14,15; Sectin 3.1; Sections 4.3,4.7–4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
21 | Run functional, integration and security tests | 5 | 20 | 40 | 44 | FR1–13; Sectionn 4.1,4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0
22 | Test speed, load, recovery and browsers | 5 | 21 | 45 | 49 | FR15; Sections 4.3–4.5,4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
23 | Run user review and correct defects | 4 | 22 | 50 | 53 | Section 4.7; all FRs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
24 | Prepare deployment and operations | 3 | 23 | 54 | 56 | Section 4.4,4.6,4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Estimated elapsed working days |  | 56
Total task-days (includes overlapping work) |  | 88
Legend:
FR = Functional Requirement
UI = User Interface
SRS = Software Requirements Specification

## Requirements and Notes
Requirements and schedule assumptions
Task # | SRS reference | Completion evidence
1 | Sections 1–4 | Team confirms feature list and acceptance criteria.
2 | Program design assignment | Tasks, durations, sequencing and dependencies are documented.
3 | FR14; UI Section 3.1 | Screen layout and navigation cover the required features.
4 | FR16; Section 3.3–3.4 | Confirm authorized API access, provider rules and payment sandbox.
5 | FR14; Section 4.6 | Agree on design and organize project files in GitHub.
6 | Program design assignment | Combine chart and wireframe in slides, record video and verify GitHub access.
7 | Section 3.3; Sections 4.1–4.2,4.5–4.6 | App, database schema, HTTPS, role controls and CI are configured.
8 | FR1 | Registration, login, logout and password protection work.
9 | FR12 | Users can change profile, password and notification preferences.
10 | FR2; Section 4.1 | Enroll, update payment method, view status and cancel in sandbox.
11 | FR4,6,16 | Retrieve movie details and supported provider availability.
12 | FR3 | Search by title and filter by genre, year, rating and provider.
13 | FR5,6 | Show poster/details and launch authorized content or provider link.
14 | FR7 | Registered users can add and remove movies.
15 | FR9 | Record accessed movies and allow history removal.
16 | FR8 | Use preferences, watchlist and viewing activity for recommendations.
17 | FR10; Section 3.4 | Notify users of watchlist availability and new recommendations.
18 | FR11 | Apply rating restrictions consistently across content access.
19 | FR13; Sectin 3.4 | Authorized staff can manage accounts, integrations and support.
20 | FR14,15; Sectin 3.1; Section 4.3,4.7–4.8 | Check consistent layout, keyboard access, labels and screen sizes.
21 | FR1–13; Section 4.1,4.6 | Test user journeys, payments, role access and provider failures.
22 | FR15; Section 4.3–4.5,4.8 | Test 3-second search target, 10,000 users, backups and recovery.
23 | Section 7; all FRs | Team reviews usability and retests corrected defects.
24 | Sections 4.4,4.6,4.8 | Configure monitoring, logs, backups and release documentation.
Source: Week 1 Assignment 2 SRS.docx, dated October 7, 2026. FR = numbered functional requirement.
Estimates are proposed planning assumptions, not instructor deadlines or actual progress. No instructor feedback was supplied.
Days measure elapsed working time for each task. Actual effort and staffing must be confirmed before using this as a committed plan.
After tasks are finish-to-start dependencies. A task starts on the working day after its latest predecessor finishes.
Rommel owns the Gantt chart and Charles owns the wireframe. Other work assignments remain for the group to agree on.
Task 4 estimates verification work only. Licensing negotiation, approval waits and unavailable provider access may extend the schedule.
Live provider access and payment credentials are prerequisites. Use test data/sandbox services for a class prototype when needed.
The SRS targets 99.9% monthly availability and recovery initiation within 30 minutes. Monitoring validates uptime after release.
Task 6 is the current program design submission. It follows design review and can run alongside application setup.
The implementation schedule estimates the full SRS scope. Adjust its timing to the syllabus and agreed prototype scope.
Change durations in column C. Start/finish formulas and bars update. Changing dependency tasks also requires updating the start formula.
Blue cells show weeks touched by a task. Exact start and finish working days are in columns E and F.